## Slide 1
Business Case
Project: Employee Self-Service Portal Implementation
Sponsor: Sarah Walker
Project Manager: Chuck Bartowski
Purpose
The purpose of this document is to present a comprehensive business case for the Employee Self-Service Portal project, outlining the objectives, benefits, costs, risks, and scope to support informed decision-making and approval.
Generated Date: 26/11/2025
Prepared By: Chuck Bartowski

## Slide 2
Business Case
Project: Employee Self-Service Portal Implementation
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Project Description
Implement a centralised Employee Self-Service (ESS) portal to allow staff to update personal details, submit leave requests, and access P&C and IT services online. The portal will reduce manual P&C processes and improve employee experience.
Business Objective
Enable employees to manage P&C and IT-related tasks online through a centralised portal, improving operational efficiency, reducing manual processing, and enhancing the employee experience.
Business Problem
Currently, P&C and IT processes are largely manual, requiring staff to submit paper forms or email requests, resulting in slow processing, frequent errors, and low staff satisfaction.
Business Objective
Operational Efficiency: Reduced P&C and IT administrative workload by automating routine tasks. Employee Satisfaction: Faster request processing and 24/7 access to self-service functions. Cost Savings: Decreased errors and manual processing time lead to financial savings. Compliance & Accuracy: Digital records improve data accuracy and support regulatory compliance.
Business Problem
P&C Department: Primary user and process owner; will benefit from reduced manual work. IT Department: Responsible for system integration, security, and support. Finance Department: Supports budgeting and tracks cost savings. Employees (End Users): All staff who will use the portal for self-service tasks. Executive Leadership Team: Oversees digital transformation strategy and benefits realisation.
Project Overview and Summary
Strategic Alignment
Achieve $200,000 Savings through Resource Efficiency ¦ Reduce operational team expenditure
Proposed Funding
Funding Source | FY25/26 | FY26/27 | TOTALS
IT Operation Budget | $300,000 | - | $300,000
People & Culture Operational Budget | - | $100,000 | $100,000
Digital Transformation Fund | - | $400,000 | $400,000
TOTALS | $300,000 | $500,000 | $800,000
Generated Date: 26/11/2025
Prepared By: Chuck Bartowski

## Slide 3
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Project Scope of Work
In Scope | Description | Assigned To | Status
Portal Design & Configuration | Build and configure the Employee Self-Service portal. | Chuck Bartowski | Open
Integration with HR Systems | Connect portal to existing HR systems (payroll, leave management). | Chuck Bartowski | Open
Integration with IT Systems | Connect portal to IT service management tools (access requests, password resets). | Chuck Bartowski | Open
User Roles & Access Management | Define roles, permissions, and authentication for employees and managers. | Chuck Bartowski | Open
Data Migration | Migrate relevant employee records required for portal functionality. | Chuck Bartowski | Open
Testing & Quality Assurance | Conduct functional testing, user acceptance testing (UAT), and security testing. | Chuck Bartowski | Open
User Training & Documentation | Provide training sessions, user guides, and FAQs for employees and HR/IT teams. | Chuck Bartowski | Open
Go-Live & Initial Support | Launch the portal and provide post-implementation support. | Chuck Bartowski | Open
Out of Scope | Description | Rating | Status
HR or IT Process Redesign | Re-engineering existing HR or IT workflows beyond portal requirements. | Chuck Bartowski | Open
New HR or IT Systems | Replacement of core HR or IT systems is not included. | Chuck Bartowski | Open
Mobile App Development | Development of native mobile apps; only web portal included. | Chuck Bartowski | Open
Third-Party Vendor Management | Managing vendors unrelated to portal integration is excluded. | Chuck Bartowski | Open
Custom Reporting | Advanced reports or BI integrations beyond standard dashboards are excluded. | Chuck Bartowski | Open
Long-Term Maintenance & Upgrades | Ongoing maintenance and system upgrades beyond initial support are excluded. | Chuck Bartowski | Open
Business Case
Project: Employee Self-Service Portal Implementation
Generated Date: 26/11/2025
Prepared By: Chuck Bartowski

## Slide 4
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Project Target Milestones
In Scope | Description | Target Date | Status
Project Kick-Off | Official start of the project; project team introduced and scope confirmed. | 9/3/2026 | Open
Idea Stage Complete | Project objectives, business case, and high-level scope approved. | 20/3/2026 | Open
Requirements Gathering Complete | All stakeholder requirements documented and signed off. | 30/3/2026 | Open
Concept Stage Complete | Conceptual design, feasibility assessment, and initial solution options approved. | 7/4/2026 | Open
Portal Design & Configuration Complete | Portal design approved and initial configuration completed. | 30/4/2026 | Open
Planning Stage Complete | Detailed project plan, timeline, budget, and resource allocation approved. | 7/5/2026 | Open
Data Migration Complete | Relevant employee records migrated to the portal. | 15/5/2026 | Open
System Integration Complete | Portal successfully integrated with HR and IT systems. | 31/5/2026 | Open
User Acceptance Testing (UAT) Complete | UAT completed; feedback collected and issues resolved. | 30/6/2026 | Open
Execution Stage Complete | All development, testing, and integration activities completed. | 15/7/2026 | Open
Training & Documentation Complete | Training sessions delivered; user guides and FAQs finalized. | 31/7/2026 | Open
Go-Live | Employee Self-Service Portal launched for all staff. | 1/8/2026 | Open
Post-Go-Live Support & Monitoring Start | Initial support phase begins; monitoring of system performance. | 2/8/2026 | Open
Project Closure | Project formally closed; final report submitted and lessons learned documented. | 23/10/2026 | Open
Closure Stage Complete | All project closure activities, including final reporting and lessons learned, completed. | 23/10/2026 | Open
Business Case
Project: Employee Self-Service Portal Implementation
Generated Date: 26/11/2025
Prepared By: Chuck Bartowski

## Slide 5
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Project Target Benefits
Business Case
Project: Employee Self-Service Portal Implementation
Benefit Type | Financial Benefit | Description | Target Amount | Timeframe
Financial | Reduced HR Processing Costs | Automation of leave requests, personal info updates, and approvals reduces manual HR workload. | $150,000 per year | Within 12 months post-launch
Financial | Reduced IT Support Effort | Self-service portal reduces routine IT tickets (password resets, access requests). | $50,000 per year | Within 12 months post-launch
Financial | Error Reduction Savings | Fewer manual errors in HR/IT requests reduce rework and administrative corrections. | $25,000 per year | Within 12 months post-launch
Non-Financial | Improved Employee Experience | Staff can submit requests online anytime without manual forms. | 90% user satisfaction rating | Within 6 months post-launch
Non-Financial | Faster Request Processing | Requests such as leave, approvals, and IT access processed in hours instead of days. | 50% reduction in processing time | Within 3 months post-launch
Non-Financial | Enhanced Data Accuracy & Compliance | Digital records ensure correct data and regulatory compliance. | Zero compliance incidents | Ongoing
Non-Financial | Increased Digital Adoption | Encourages staff to embrace digital workplace tools. | 80% of staff actively using portal | Within 6 months post-launch
Non-Financial | Management Visibility & Reporting | Real-time dashboards for HR and IT teams improve decision-making. | Monthly reporting dashboards operational | Within 3 months post-launch
Generated Date: 26/11/2025
Prepared By: Chuck Bartowski

## Slide 6
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Project Identified Risks
Business Case
Project: Employee Self-Service Portal Implementation
Risk Profile | Description | Rating | Status
Adverse Weather Delays | Heavy rainfall may delay resurfacing and curing times. | High | Open
Material Supply Constraints | Asphalt supply shortages could delay progress. | Medium | Open
Traffic Diversion Impacts | Congestion across alternative routes may increase public complaints. | Medium | Open
Safety Incidents | Worker or motorist injury during nightworks activities. | High | Open
Subsurface Structural Defects | Unexpected repairs required after pavement removal. | High | Open
Project Identified Assumptions
Assumptions | Description | Rating | Status
Access windows approved | Nightwork access granted by Transport for NSW throughout construction. | High | Open
Weather remains within seasonal norms | Extreme weather events will not exceed forecast averages. | Medium | Open
Supplier continuity | Contracted vendors will deliver materials on time. | Medium | Open
Community notifications sufficient | Public awareness campaigns will reduce disruption. | Low | Open
Regulatory standards unchanged | No major compliance changes during project. | High | Open
Generated Date: 26/11/2025
Prepared By: Chuck Bartowski

## Slide 7
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Business Case Approvals
Business Case
Project: Employee Self-Service Portal Implementation
Role | Name | Approval Status | Approved Date | Approval Forum
Project Sponsor | Sarah Walker | Approved | 1 November 2025 | Executive Steering Committee
Senior Project Manager | Chuck Bartowski | Approved | 1 November 2025 | Internal Project Control Group (PCG)
Finance Business Partner | Leif Diao | Approved | 1 November 2025 | Finance Governance Forum
Engineering Lead | Daniel Owen | Pending |  | Technical Review Board
Safety & Compliance Manager | Sarah Parkes | Approved | 1 November 2025 | Safety & Risk Committee
Generated Date: 26/11/2025
Prepared By: Chuck Bartowski