## Slide 1
Lesson Learned
This is a generated list of Lesson Learned across IT Project Templates they may be applicable for your project
Generated for Project: Employee Self-Service Portal Implementation
Generated Date: 26/11/2025
Generated by ALBERT

## Slide 2
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Lessons Learned
Project | Lesson Learned Title | Date Raised | Category | Assessment | Project Stage | Challenge | Impact | Recommendation
Cloud Adoption and Migration Project | Automated backups prevented data loss | 10/12/2025 | Security | Positive | 4. Execution | Risk of accidental deletion | Minimal downtime | Enable automated backups before migration
Cloud Adoption and Migration Project | Vendor support improved issue resolution | 15/12/2025 | Supply Chain | Positive | 4. Execution | Complex cloud issues | Faster problem resolution | Maintain good vendor relationships
Cloud Adoption and Migration Project | Cloud monitoring tools reduced outages | 18/12/2025 | Environment | Positive | 4. Execution | Unnoticed downtime | Better system reliability | Deploy monitoring tools early
Cloud Adoption and Migration Project | Insufficient user training | 20/12/2025 | Stakeholders | Negative | 4. Execution | Users unfamiliar with cloud | Increased support tickets | Provide comprehensive training sessions
Cloud Adoption and Migration Project | Network bandwidth underestimated | 12/12/2025 | Environment | Negative | 3. Planning | Large data transfer | Delayed migration | Test bandwidth and optimize transfer schedule
Cloud Adoption and Migration Project | Clear migration roadmap | 25/12/2025 | Business Systems | Positive | 3. Planning | Complexity of migration | Smooth execution | Develop detailed step-by-step migration plan
Cloud Adoption and Migration Project | Licensing costs underestimated | 28/12/2025 | Legal | Negative | 3. Planning | Cloud subscription costs | Budget overrun | Conduct detailed licensing assessment
Intranet | User surveys improved content relevance | 10/11/2025 | Stakeholders | Positive | 5. Closure | Irrelevant content | Higher usage | Conduct surveys regularly
Intranet | Gamification increased engagement | 5/11/2025 | Stakeholders | Positive | 4. Execution | Low employee participation | Higher usage | Introduce badges and recognition
Intranet | Search functionality was poor | 7/11/2025 | Business Systems | Negative | 4. Execution | Users couldn’t find content | Reduced adoption | Improve search algorithm and indexing
Intranet | File version issues | 12/11/2025 | Information Management | Negative | 4. Execution | Overwriting documents | Lost information | Implement version control system
Intranet | Personalized content increased engagement | 15/11/2025 | Business Systems | Positive | 4. Execution | Generic content | Higher usage | Personalize content for target users
Intranet | Broken links reduced credibility | 18/11/2025 | Information Management | Negative | 4. Execution | Outdated URLs | User frustration | Implement link validation tool
Project Management - External | Late contract review caused delays | 18/10/2025 | Legal | Negative | 2. Concept | Unclear terms | Project postponement | Review contracts early with legal team
Project Management - External | Vendor delays affected timelines | 7/10/2025 | Supply Chain | Negative | 4. Execution | Dependencies on third parties | Schedule slippage | Include buffer for vendor delays
Project Management - External | Stakeholder newsletters improved engagement | 10/10/2025 | Communication | Positive | 4. Execution | Multiple stakeholders | Better informed decisions | Regular communication with newsletters
Project Management - External | Clear roles improved accountability | 5/10/2025 | Stakeholders | Positive | 3. Planning | Team confusion on responsibilities | Tasks completed on time | Define roles and responsibilities early
Project Management - External | Misalignment of KPIs | 12/10/2025 | Business Systems | Negative | 3. Planning | Conflicting metrics | Confusion in reporting | Align KPIs before execution
Project Management - External | Risk register improved transparency | 15/10/2025 | Business Systems | Positive | 3. Planning | Lack of risk awareness | Reduced surprises | Maintain detailed risk register
Generated Date: 26/11/2025
Generated by ALBERT
Lessons Learned for IT Projects
Project: Employee Self-Service Portal Implementation

## Slide 3
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Project | Lesson Learned Title | Date Raised | Category | Assessment | Project Stage | Challenge | Impact | Recommendation
Resource Management | Custom dashboards improved reporting | 5/9/2025 | Business Systems | Positive | 4. Execution | Manual reporting errors | Faster decision making | Build dashboards during planning
Resource Management | Integration with payroll delayed | 7/9/2025 | Supply Chain | Negative | 4. Execution | Complex data mapping | Payroll errors | Test integration before rollout
Resource Management | Data duplication errors | 12/9/2025 | Information Management | Negative | 4. Execution | Conflicting resource data | Reporting inaccuracies | Cleanse and validate data before use
Resource Management | Automated alerts improved deadlines | 15/9/2025 | Business Systems | Positive | 4. Execution | Manual tracking of tasks | On-time completion | Set up automated notifications
Resource Management | Delayed approvals slowed process | 18/9/2025 | Stakeholders | Negative | 4. Execution | Manager response time | Resource bottlenecks | Automate approval workflows where possible
Resource Management | Resource allocation visibility | 10/9/2025 | Business Systems | Positive | 3. Planning | Lack of clarity on assignments | Improved planning | Implement centralized dashboard
SharePoint Online Migration | User feedback sessions | 7/5/2025 | Stakeholders | Positive | 5. Closure | Ensuring user satisfaction | Improved adoption | Conduct structured feedback surveys
SharePoint Online Migration | Version control improved collaboration | 5/5/2025 | Business Systems | Positive | 4. Execution | Multiple contributors editing files | Reduced conflicts | Implement version control early
SharePoint Online Migration | Migration downtime underestimated | 6/5/2025 | Environment | Negative | 4. Execution | Scheduling during work hours | User frustration | Plan migration during low-traffic periods
SharePoint Online Migration | Metadata tagging inconsistent | 12/5/2025 | Information Management | Negative | 4. Execution | Inconsistent content | Difficult to retrieve documents | Standardize metadata fields before migration
SharePoint Online Migration | Training improved end-user confidence | 15/5/2025 | Stakeholders | Positive | 4. Execution | Users unfamiliar with system | Higher adoption | Conduct hands-on workshops
SharePoint Online Migration | Governance framework helped compliance | 10/5/2025 | Legal | Positive | 3. Planning | Multiple departments | Reduced risk of non-compliance | Implement governance framework early
Website Integration | Cross-browser testing | 15/6/2025 | Environment | Positive | 4. Execution | Different browser behaviors | Stable user experience | Test on all supported browsers
Website Integration | Legacy system conflicts | 22/6/2025 | Business Systems | Negative | 4. Execution | Old integrations incompatible | Project delays | Assess legacy systems early
Website Integration | Modular coding improved maintainability | 25/6/2025 | Business Systems | Positive | 4. Execution | Complex legacy code | Easier future updates | Use modular approach in development
Website Integration | Data mapping errors | 28/6/2025 | Information Management | Negative | 4. Execution | Misaligned data fields | Integration issues | Validate mapping rules before integration
Website Integration | Scope creep due to extra features | 18/6/2025 | Business Systems | Negative | 3. Planning | Changing client requirements | Delays and cost overruns | Clearly define scope and freeze requirements
Website Integration | Clear technical documentation | 20/6/2025 | Information Management | Positive | 3. Planning | Multiple developers | Reduced errors | Prepare detailed documentation before development
Website Refresh | Early prototyping saved rework | 22/7/2025 | Business Systems | Positive | 2. Concept | Unclear design requirements | Reduced rework | Prototype key components early
Website Refresh | Improved SEO increased traffic | 10/7/2025 | Business Systems | Positive | 4. Execution | Content optimization | Higher engagement | Include SEO planning in project design
Generated Date: 26/11/2025
Generated by ALBERT
Lessons Learned for IT Projects
Project: Employee Self-Service Portal Implementation
Lessons Learned

## Slide 4
Program | Portfolio | Business Unit | Sponsor | Proposed Start Date | Proposed End Date
Digital Transformation Program | Digital Transformation | Digital Services | Sarah Walker | 9-Mar-2026 | 23-Oct-2026
Project | Lesson Learned Title | Date Raised | Category | Assessment | Project Stage | Challenge | Impact | Recommendation
Website Refresh | Insufficient load testing | 12/7/2025 | Environment | Negative | 4. Execution | High visitor traffic | Slow site performance | Conduct performance testing under load
Website Refresh | Delays due to last-minute content | 18/7/2025 | Communication | Negative | 4. Execution | Late content delivery | Launch delayed | Set content deadlines earlier in project
Website Refresh | Accessibility overlooked | 25/7/2025 | Legal | Negative | 4. Execution | WCAG compliance | Legal and user issues | Conduct accessibility testing before launch
Website Refresh | User analytics guided design | 15/7/2025 | Business Systems | Positive | 3. Planning | Understanding user behavior | Better engagement | Use analytics to inform design decisions
Generated Date: 26/11/2025
Generated by ALBERT
Lessons Learned for IT Projects
Project: Employee Self-Service Portal Implementation
Lessons Learned