## Slide 1
Stage | Program | Portfolio | Business Unit | Start Date | End Date
5. Closure | Construction Development | Infrastructure | Project Management Office | 26-Feb-25 | 31-Dec-26
 | Overall | Schedule | Financial | Risks |  | Issues | Resources | Scope | Change
Current | R | A | G | G |  | R | G | G | G
Previous | G | G | G | G |  | G | G | G | G
Overall Health Comments |  |  |  |  | Go to Green Comments |  |  |  | 
This ppt is auto-generated every Friday at midday and or generated based on a trigger. The file is auto-generated to the nominated document location and has flexibility to also notify sponsors in teams or email if there are items that require attention for the sponsors or executives |  |  |  |  | This ppt is auto-generated every Friday at midday and or generated based on a trigger. The file is auto-generated to the nominated document location and has flexibility to also notify sponsors in teams or email if there are items that require attention for the sponsors or executives |  |  |  | 
Summary | Budget | Actuals | ETC | EAC | Variance
Whole of Life | $15,831,990 | $8,201,366 | $4,590,225 | $12,791,591 | $3,040,399
Current Year | $3,664,900 | $926,438 | $901,705 | $1,828,143 | $1,836,757
Open Risks | Due Date | Rating
Procurement delay.. | 10/07/2025 | Extreme
Schedule extension.. | 01/10/205 | Extreme
Resourcing issues | 10/07/2025 | Extreme
 | 01/10/205 | Moderate
 | 10/07/2025 | Low
Generated Date: 26/11/2025
The Sydney Harbour Bridge is undergoing critical resurfacing works to maintain the structural integrity and safety of one of Australia’s most iconic transport links. This project involves the removal and replacement of aging road surfaces across the main deck to ensure a smoother, safer journey for the thousands of vehicles that cross daily.
Open Issues | Due Date | Rating
Contractor OH&S expiry and inability to renew | 10/12/2025 | Extreme
Run out of budget | 05/01/2026 | Moderate
Consultant or contractor delays | 05/01/2026 | Moderate
Lack of Stakeholder Engagement | 05/01/2026 | Low
Open Milestones | Due Date | Rating
Milestone 1 | 10/10/2025 | Overdue
Milestone 2 | 15/10/2025 | Overdue
Milestone 3 | 10/12/2025 | Upcoming
Milestone 4 | 01/02/205 | Upcoming
Milestone 5 | 10/02/2025 | Upcoming
Generated By: Chuck Bartowski
Legend: Text Color: On Track, Late, Overdue
Project Manager: Chuck Bartowski
Activities Completed this Period | Actions Planned for Next Period
this ppt is auto-generated every Friday at midday and or generated based on a trigger. The file is auto-generated to the nominated document location and has flexibility to also notify sponsors in teams or email if there are items that require | This ppt is auto-generated every Friday at midday and or generated based on a trigger. The file is auto-generated to the nominated document location and has flexibility to also notify sponsors in teams or email if there are items that require attention for the sponsors or executives
Report Period
NOV 2025
Project Status Report
Project: Sydney Harbour Bridge Resurfacing